| Semester: Maximum Marks: 50 Examination: ATKT Exam Date: 29th Aug 2024 Duration: Hours 2.5 |  |  |
| --- | --- | --- |
| Program code: Program: Godrej and Boyce PGDM OPS and SCM | Class: | Semester/Trimester: |
| College: K. J. Somaiya Institute of Management | Name of the department/Section/Center: Operations and Supply Change Management |  |
| Course Code: 117I19C106 | Name of the Course: Project Management |  |
| Instructions: Question 1 is compulsory. Answer any four from Q2 to Q7 |  |  |

| Question No. |  | Max. Marks |
| --- | --- | --- |
| 1 | Under Malabar Hill, there is a century old reservoir which supplies water to entire south Mumbai. BMC wants to rebuild that reservoir as structural stability of that reservoir is questionable as per BMC. During re-building of that reservoir famous “Hanging Gardens” which sits on top of this reservoir will be off-limits for several years. Also, water needs to be supplied for entire South Mumbai through alternate means. There is a strong opposition to this project by residents as they will not be able to visit “Hanging Gardens”. Environmentalists and nature lovers are up in arms as hundreds of trees will be cut. Section of the population feels that there is no need to rebuild the reservoir as it is in good shape and minor repairs can do the job. Malabar Hill is home to richest population in Mumbai with many top Industrialists, Corporate executives and ministers living in this area. BMC has hired you as Project Management Consultant for this project and asked you to prepare a Project Charter Document for submission for public hearing. Please prepare Project charter with following paragraphs - Project Purpose or Justification - High-level Project description and boundaries - High-level Requirements - Assumptions and constraints - High-level risks - Summary milestone Schedule - Summary Budget - Stakeholder list | 10 |
| 2 | Activity and Precedence list along with “Expected Time” for completion and variance is given in below table Activity; Predecessor; Expected Time; Variance. A; -; 2; 2/6. B; -; 3; 2/6. C; A; 2; 4/6. D; B; 4; 4/6. E; C; 4; 2/6. F; C; 3; 1/6. G; D, E; 5; 1/6. - Draw project network diagram - Calculate Project Duration - Identify critical path - What is project variance and standard deviation? - What is the probability that project will be completed in 15 weeks? - Z value table is given in annexure I | 10 |
| 3 | Activity and Precedence list along with Normal Time, Crash Time, Normal Cost and Crash Cost are as given below Activity; Predecessor; Normal Time (Months); Crash Time (Months); Normal Cost $; Crash Cost $. A; -; 10; 8; 2000; 2400. B; -; 7; 5; 3000; 3500. C; A; 9; 8; 1000; 1300. D; B; 6; 4; 2000; 2600. E; D; 9; 8; 8800; 9000. - Please draw project network diagram - Calculate project duration - Identify critical path - Determine the least cost to crash project by 3 months - Can we crash the project beyond 3 months? If yes, how much and at what cost? - What is the best possible crash schedule and cost for it? | 10 |

| 4 | A project with duration of 20 weeks was reviewed at the end of 10 weeks with status as follows Week; Cumulative Planned Completion; Cumulative Actual Completion; Weekly Planned cost Budget; Weekly Actual cost incurred. 1; 5%; 4%; 100; 120. 2; 10%; 7%; 100; 150. 3; 15%; 12%; 100; 100. 4; 20%; 15%; 100; 110. 5; 25%; 20%; 100; 130. 6; 30%; 23%; 100; 140. 7; 35%; 25%; 100; 100. 8; 40%; 25%; 100; 170. 9; 45%; 30%; 100; 80. 10; 50%; 35%; 100; 90. 11; 55%; 100. 12; 60%; 100. 13; 65%; 100. 14; 70%; 100. 15; 75%; 100. 16; 80%; 100. 17; 85%; 100. 18; 90%; 100. 19; 95%; 100. 20; 100%; 100. Calculate - Schedule Variance - Cost variance - Schedule Performance Index (SPI) - Cost Performance Index (CPI) - Expected time to complete (ETC) - Expected cost at complete (EAC) | 10 |
| --- | --- | --- |
| 5 | Write short notes on any two - What is the difference between Project, Program and Portfolio? Please explain with example - What is FMEA? Please explain methodology of FMEA with an example - What is PESTEL analysis? Please explain with an example | 10 |
| 6 | Somaiya School is organizing a Fun Fair for their school students, and they want to install Ferris wheel on the day. However, school management is worried about safety of the wheel and has requested KJSIM to do Safety Assessment. KJSIM in turn assigned few students who are trained in FMEA technique in Project Management subject to undertake this task and give their recommendations. Please list various failure modes, calculate their RPN number, propose countermeasures and recalculate RPN number after implementing those countermeasures At the end, please recommend if school should go ahead with Ferris wheel or not based on your assessment of FMEA | 10 |
| 7 | Please explain what triple constraint is in a project. Please explain what happens on other parameters when any one of the parameters of STQC is changed? | 10 |

Annexure I